## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Color
Cool Contacts
LAMP Stack Application |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned |  |  |  |  | Goal -> Red Diamond | [5 empty] | Milestone -> Yellow Flag
Prof. Leinecker
Project Start Date: | 2021-08-25 |  |  |  |  | August | [6 empty] | September | [27 empty] | October
Scrolling Increment: | 5 | time axis 2021-08-30 to 2021-10-24
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-08-30 to 2021-10-24
Database Configuration
Task 1 | Goal | Name | 25% | 2021-08-25 | 20 | 2021-08-30: 2; 2021-08-31: 2; 2021-09-01: 2; 2021-09-02: 2; 2021-09-03: 2; 2021-09-04: 2; 2021-09-05: 2; 2021-09-06: 2; 2021-09-07: 2; 2021-09-08: 2; 2021-09-09: 2; 2021-09-10: 2; 2021-09-11: 2; 2021-09-12: 2; 2021-09-13: 2
Task 2 | Milestone |  |  | 2021-08-30 | 1 | bar: 2021-08-30
Task 3 | Low Risk |  | 1% | 2021-08-22 | 10
Task 4 | Milestone |  |  | 2021-09-14 | 1 | bar: 2021-09-14
Task 5 | Med Risk |  | 1% | 2021-08-31 | 6
Rest-API Build
Login (Credential Check) | High Risk | Kier Fretenborough | 1% | 2021-08-31 | 13
Create User (Add Credentials) | On Track |  | 1% | 2021-09-02 | 9
Search Contacts | Low Risk |  | 1% | 2021-09-07 | 11
Task 4 | Milestone |  |  | 2021-09-09 | 1 | bar: 2021-09-09
Task 5 |  |  |  | 2021-09-10 | 24
Front-End Deployment
Static Login Page | On Track | Anthony Garcia | 1% | 2021-09-09 | 4
Task 2 | Med Risk |  |  | 2021-09-12 | 14
Task 3 | On Track |  |  | 2021-09-27 | 6
Task 4 | Goal |  |  | 2021-10-01 | 3 | 2021-10-01: 2; 2021-10-02: 2; 2021-10-03: 2
Task 5 | Low Risk |  |  | 2021-08-31 | 19
Documentation
Entity Relationship Diagram |  |  |  | 2021-10-04 | 15
Use Case Diagram |  |  |  | 2021-10-18 | 5
PowerPoint Slides | Milestone |  |  | 2021-11-29 | 1
Gantt Chart
To add more data, Insert new rows ABOVE this one

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-08-25 |  |  |  |  | August | [6 empty] | September | [34 empty] | October
Scrolling Increment: | 1 | time axis 2021-08-26 to 2021-10-20
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-08-26 to 2021-10-20
TITLE 1
Task 1 | Goal | Name | 25% | 2021-08-25 | 3 | 2021-08-26: 2; 2021-08-27: 2
Task 2 | Milestone |  |  | 2021-08-30 | 1 | bar: 2021-08-30
Task 3 | Low Risk |  | 50% | 2021-08-22 | 10
Task 4 | Milestone |  |  | 2021-09-14 | 1 | bar: 2021-09-14
Task 5 | Med Risk |  | 10% | 2021-08-31 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-08-31 | 13
Task 2 | On Track |  | 50% | 2021-09-02 | 9
Task 3 | Low Risk |  | 33% | 2021-09-07 | 11
Task 4 | Milestone |  |  | 2021-09-09 | 1 | bar: 2021-09-09
Task 5 |  |  |  | 2021-09-10 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-09-09 | 4
Task 2 | Med Risk |  |  | 2021-09-12 | 14
Task 3 | On Track |  |  | 2021-09-27 | 6
Task 4 | Goal |  |  | 2021-10-01 | 3 | 2021-10-01: 2; 2021-10-02: 2; 2021-10-03: 2
Task 5 | Low Risk |  |  | 2021-08-31 | 19
TITLE 4
Task 1 |  |  |  | 2021-10-04 | 15
Task 2 |  |  |  | 2021-10-18 | 5
Task 3 | Milestone |  |  | 2021-11-29 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one